Draft SCYP Report Writing Timeline— Summer 2026

The report writing process starts immediately after the term ends for your SCYP course. It is easier to start gathering information from your peers and professor(s) before your class ends; for example, you may want to download shared files from Canvas, collect student names and majors, or collect final products (such as InDesign Files, presentations, or reports) from individual students or student groups. Ask for the highest resolution images and files possible.

SCI can be flexible regarding due dates if you communicate early. If you experience trouble during any part of this process, please reach out to the SCI Report Coordinator. You are welcome to complete any parts of the report earlier than the deadlines below.

Before the Term

- Gather images and final reports from class

- Coordinate with professor to ensure materials are adequate and high quality

Week 1: June 15 – 19

- Gather any remaining images/other resources needed for the report by EOD Wednesday, June 17.

- Report outline due via email by Friday, June 19.

Week 2: June 22 – 26

- Report Coordinator provides outline feedback by EOD, Monday, June 22.

- Begin the report's first draft, using text placeholders for figures as needed. Focus on content, not formatting

Weeks 3 and 4: June 29 – July 10

- Report first draft due via email by EOD, Monday, June 29.

- Report coordinator provides first draft feedback no later than EOD, Wednesday, July 8.

Week 5: July 13 – July 17

- Incorporate feedback and continue developing report draft 2.

- Complete any incomplete sections.

- Include all image placeholders.

Week 6: July 20 – 24

- Report second draft due via email by EOD, Monday, July 20.

- Report Coordinator provides feedback no later than EOD, Wednesday, July 22.

- Incorporate feedback and complete final touches.

Week 7: July 27 – 31

- Third, and final draft due via email by Monday, July 27.

- SCI Graphic Designer formats report in InDesign

Week 8: August 3 – 7

- Final draft InDesign report reviewed by SCI staff; sent to city staff and professor(s) for review by Friday, August 7.

Week 9: August 10 – 14

- Report comments received by city staff and professor no later than Friday, August 14.

- Request edits from report writer if necessary

- Complete final edits

Weeks 10: August 17 – 21

- Send final report to UO Printing & Mailing

- Publish and distribute final report